## Per Funding
[10 empty] | ANNEXURE B |  |  | "ANNEXURE C" |  | ANNEXURE B
2011/2012 ROLL - 1ST ROLL-OVER ADJUSTMENT BUDGET - OPERATING PROJECTS
DIRECTORATE | COST CENTRE DESCRIPTION |  | PROJECT DESCRIPTION | 2011/2012 | 2011/2012 | 2011/2012 | COMMENTS |  |  |  | 2011/2012 | 2011/2012
|  | COST |  | APPROVED | BUDGET | 1st ROLL-OVER |  | PROJECT STATUS phase as at 31 December 2011 (e.g. Contract not awarded, contract awarded, project on site, design phase, tender etc.) | REASONS why spending Is not 50%: Name key challenges | TIME PERIOD to complete the project |  | MID YEAR | Comments | REASONS why spending Is not 50%: Name key challenges | TIME PERIOD to complete the project
|  | CENTRE |  | BUDGET | ADJUSTMENTS | ADJ. BUDGET |  |  |  |  | ADJUSTMENTS | BUDGET
1. BCMET c/o
Development Facilitation and Partnership | Transport Planning and Operations Admin | 620005 | Transport planning c/o | 0 | 204382.5 | 204382.5 |  | Consultant has been appointed and work has commenced | Progress stalled due to Councilors not being appointed to Project Steering Committee over period of Local Elections | Project to be completed by December 2011 |  | 204382.5
Development Facilitation and Partnership | Transport Planning and Operations Admin | 620005 | Transport policy and by-law | 0 | 400000 | 400000 |  | New Funding | New Funding | New Funding |  | 400000
|  |  |  | 0 | 604382.5 | 604382.5 | 0 |  |  |  | 0 | 604382.5
2. Department of Environmental Affairs and Tourism c/o
Development Facilitation and Partnership | Local Economic Development | 635005 | Intlanzi eKoloni (DEDEA Funds) | 140000 |  | 140000 | [5 empty] | 140000
|  |  |  | 140000 |  | 140000 | 0 |  |  |  | 0 | 140000
3. Disaster Management Fund c/o
Municipal Services | Fire and Rescue Services | 725010 | Risk & Vulnerability Assessment c/o | 96999 | -96999 | 0 |  | Correcting wrong Cost Centre | Correcting wrong Cost Centre | Correcting wrong Cost Centre |  | 0
Municipal Services | Fire and Rescue Services | 725055 | Risk & Vulnerability Assessment c/o | 0 | 96999 | 96999 |  | Evaluation phase, tender closed 24 June 2011 | Project in progress. | March 2012 |  | 96999
|  |  |  | 96999 | 0 | 96999 |  |  |  |  | 0 | 96999
4. Local Government and Traditional Affairs c/o
Finance and Support Services | Supply Chain Management | 320010 | Overview of Internal Controls - SCM | 0 | 12135 | 12135 |  | Design phase | Funds to be used in conjunction with SCM Turnaround project | Funds will be spent before FYE |  | 12135
Development Planning and Management | City Planning | 615070 | Informal Settlement Study & Implementation Programme c/o | 0 | 300000 | 300000 |  | Service Providers were appointed. The categorisation and classification of informal settlements has been completed. Project team in process of drafting draft report and implementation programme. Balance of project to be paid on completion of the project. | Project was delayed by more than 18 months due to the non-existence of Project Steering Committees due to political instability. | Project to be completed by February 2012 and submit to Council for approval in March of 2012. | -245376 | 54624 | Project completed and final PSC meeting held on 10 November 2011. A report to be submitted to Council for adoption in the beginning of 2012. | Balance of R245,376 to be used for Phase 2 Land Identification for relocation of the high priority informal settlements identified in study | Balance of R245,376 to be used for Phase 2 Land Identification for relocation of the high priority informal settlements identified in study
Development Planning and Management | City Planning | 615070 | Mdantsane LSDF c/o | 0 | 414857 | 414857 |  | Service Provider appointed and Situation Analysis completed (Phase 1) and Key Spatial Development Proposals (Phase 2) developed and to be be presented to a Project Steering Committee and Stakeholders meeting in near future. | The project has been delayed due to the fact that no Project Steering Committee (chaired by the Portfolia Councillor) has taken place since scince October 2010. A PSC meeting and a stakeholders meeting was scheduled for March 2011 was cancelled due to the upcoming election and has not taken place since. | The project is intended to be completed by end of 2011/2012 FY | -55889 | 358968 | PSC meeting held on 11 Nov 2011. Next PSC to be held early in 2012 and then a Public Meeting to be held with all relevant stakeholders. Data Analysis complete and Spatial Proposals have been completed in draft process. | Final report to be completed in April 2012 and then to be submitted to Council for approval . | Final report to be completed in April 2012 and then to be submitted to Council for approval .
Development Planning and Management | City Planning | 615070 | Planning - Needscamp c/o | 0 | 58036 | 58036 |  | Service Providers appointed. Settlement Planning component completed. Awaiting MEC approval when land ownership i.e. Section 28 Certificate from Department of Land Affairs has been resolved before final payment can be made to Service Providers. Payments done in previuous financial years. | MEC approval is outstanding for a few yesrs | Will be completed once MEC has approved it |  | 58036
Development Planning and Management | City Planning | 615070 | Settlement upgrading of Yellowwood c/o | 0 | 471845 | 471845 |  | Service Providers appointed. Settlement Planning component completed. Awaiting MEC final approval which can only be given when land ownership has been resolved with Department of Land Affairs. Only when MECs approval has been given can final payment be made to Service Providers. Payments done in previous financial years. | MEC approval is outstanding for a few yesrs | Will be completed once MEC has approved it | -431845 | 40000 | Settlement Planning Component Completed. Awaiting MEC final approval which can only be given when land ownership has been resolved by Dept od Land Affairs. Only MEC's approval has been given can final payment be made to service providers. | Balance of R431,845 will be utilised for the next phase, which is the cadastral survey. Therefore the balance will be transferred to the Land Surveying Cost Centre through the Adjustment Budget. | Balance of R431,845 will be utilised for the next phase, which is the cadastral survey. Therefore the balance will be transferred to the Land Surveying Cost Centre through the Adjustment Budget.
|  |  |  | 0 | 1256873 | 1256873 |  |  |  |  | -733110 | 523763
5. Department of Water Affairs and Forestry - DoRA
Municipal Services | Water, Sanitation and Scientific services | 520005 | Water Services Operating & Transfer Subsidy | 1680000 |  | 1680000 | Roll Overs from 2009/10 |  |  |  | 34000 | 1714000 | As Per Revised DoRA Allocations (HR costs in terms of transfers and O&M on DWA transferred infrastructure)
Municipal Services | Water, Sanitation and Scientific services | 520005 | Water Services Capacity Building Business Plan | 1150000 |  | 1150000 | Roll Overs from 2009/10 |  |  |  |  | 1150000
|  |  |  | 2830000 | 0 | 2830000 |  |  |  |  | 34000 | 2864000
6. Department of Water Affairs and Forestry - DoRA c/o
Municipal Services | Water, Sanitation and Scientific services | 520005 | Water Services Operating & Transfer Subsidy | 0 |  | 0 |  |  |  |  | 4000 | 4000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 4000 | 4000
7. Department of Water Affairs and Forestry- Provincial
Municipal Services | Water, Sanitation and Scientific services | 520005 | East Bank WWTW | 6945000 |  | 6945000 | Roll Overs from 2009/10 |  |  |  | 5689085 | 12634085 | Additional Funding received from DWAF - Province
Municipal Services | Water, Sanitation and Scientific services | 520005 | Dimbaza WWTW | 450000 |  | 450000 | [5 empty] | 450000
Municipal Services | Water, Sanitation and Scientific services | 520005 | Water Connservation & Demand Management | 5000000 |  | 5000000 | [5 empty] | 5000000
|  |  |  | 12395000 | 0 | 12395000 |  |  |  |  | 5689085 | 18084085
8. DLGTA c/o
Strategic Management | Municipal Manager and Support Services | 205005 | Muncipal Manager and Support Services (Elections) | 0 | 201327.09 | 201327.09 | Roll Overs from 2009/10 |  |  |  | 100000 | 301327.09 | Additional Funding not on the Budget
Strategic Management | Municipal Manager and Support Services | 205005 | Local Government Elections Financial Assistance | 0 | 2367523.83 | 2367523.83 | [5 empty] | 2367523.83
Municipal Services | Mdantsane Urban Renewal Unit | 255010 | Mdantsane ICT Centre c/o | 0 | 391649.2 | 391649.2 |  | Contract awarded. | The project is ongoing and is implemented in phases. The project is in the fourth phase of its implementation. | The rolled-over funds will be completed |  | 391649.2
Municipal Services | DVRI | 250005 | DV Stakeholder Mobilisation c/o | 0 | 81222.05 | 81222.05 |  | Project has been completed. The remaining funds will be utilised to cunduct Stakeholder's Forum meetings . | The appointment amount for the service provider as well as operating costs during project implementation period, were below the budget available. | 2012-06-01 |  | 81222.05
Municipal Services | DVRI | 250005 | DVRI Business Plan | 0 | 712313.51 | 712313.51 |  | The tender has been readvertised for the third time. | The procurement of a service provider has not been finalised due to readvertisement of the tender for three times based on the following reasons: 1). the recommended bidder had an invalid tax clearance certificate and couldnt provide a valid one. 2). The bids recieved quoted above the budget available. 3). The tender documents couldn't be accessed by bidders at SCM due to the internal strike action and that adversely affected the procurement process. 4). All bidders were non-responsive. | The tender will be cancelled and readvertised during the second quarter of the FY. Subsequently, the project will be implemented for a duration of 3 months and therefore the budget available will be utilised by end of June 2012 | -200000 | 512313.51 | Award delayed due to non responsive tenders and re-tender resulting in the possibility that the project may not be completed in current financial year. Tbc after award.
Municipal Services | DVRI | 250005 | DV Quality of Life Survey c/o | 0 | 300000 | 300000 |  | The DVRI Steering Committee resolved that the budget must be reallocated to the DV ICT Center project as one of the priority issues for consideration. The request to reallocate funding has been submitted to the funder (DLGTA) for approval. | The funding reallocation request has only been approved in principle in 09 Sept 11 subject to submission of a council resolution on the matter. | During the current financial year it is envisaged that only 50% of the budget will be utilised, due to the council resolution required by DLGTA as well as procurement process to be undertaken once the funding has been fully reallocated, aligned with municipal budget adjustment processes. |  | 300000
Finance and Support Services | Office of the Director of Finance | 305005 | Internal Control | 0 | 500000 | 500000 |  |  |  |  | -500000 | 0 | Project Funded by Finance Management Grant. Installation of the SCM access boom gates, Development of SCM Process Procedure and flowchart Manuals.
Development Planning and Management | City Planning | 615070 | Mdantsane Infill Areas - Phase III | 0 | 228437.5 | 228437.5 |  | Service Providers appointed. Project Phase 1 completed and approved by Council end of 2010. Phase 2: "Land idendification study for the relocation of Infill in Mdantsane". Appointments where done in March 2011 and busy with stage 2 and draft report: "On -Site Verification of Land Parcels" has been submitted to BCMM for comments by BCMM. Invoice of R 38 688 has been submitted to BCMM for payment. Can only be paid once roll-overs have been approved. | As phase 1 was only approved by Council end of 2010 and phase 2 commenced only in 2011. No challenges | Project to be completed by end of December 2011 | -125339 | 103098.5 | Project Completed. Report to be submitted to Council for adoption in beginning of 2012 | Balance of R115,320 to be used for detailed layout planning of BCMM owned land parcels which were identified in this study/project Phase2 | Balance of R115,320 to be used for detailed layout planning of BCMM owned land parcels which were identified in this study/project Phase2
Development Facilitation and Partnership | Local Economic Development | 635005 | Mdantsane Skills Audit c/o | 0 | 322908.22 | 322908.22 | [5 empty] | 322908.22
|  |  |  | 0 | 5105381.4 | 5105381.4 |  |  |  |  | -725339 | 4380042.4
9. European Commission c/o
Municipal Services | Internments | 755025 | Clearing of Cemetries | 0 | 73242.14 | 73242.14 |  | A roll over has been requested to continue project | The project is ongoing . Participants to be engaged | The rolled over funds will be completed |  | 73242.14
Municipal Services | Mdantsane Urban Renewal Unit | 255010 | ICT Centre c/o | 0 | 222180.84 | 222180.84 |  | Contract awarded. | The project is ongoing and is implemented in phases. The project is in the fourth phase of its implementation. | The rolled-over funds will be completed |  | 222180.84
Municipal Services | Mdantsane Urban Renewal Unit | 255010 | Street Naming Phase 1 c/o | 0 | 209702.22 | 209702.22 |  | Database of names for neighbourhoods and higher order roads has been developed and is awating approval from the Project Steering Committee. | Phase three of the project has not been completed as a result of a meeting with neighbourhood 4 that could not convene. This resulted in the Service Provider not being paid the remaining amount for phase three. | The project is still on hold and the remaining funds for the project will be utilized once the project implementation has commenced. |  | 209702.22
Development Facilitation and Partnership | Local Economic Development | 635005 | Hydro-ponics - MDT | 0 | 119002.04 | 119002.04 |  | The funds are to be used to equip the packshed at NU 18 Mdantsane, which will be completed by End October 2011 | Currently in the process of completing the construction of the packshed and will therefore procure the operational equipment through informal tender | 1 month after budget Approval by Council |  | 119002.04
Development Facilitation and Partnership | Local Economic Development | 635005 | LIFE - Livelihoods and Innovation Fund Enhancement | 0 | 27355.55 | 27355.55 | [5 empty] | 27355.55
Municipal Services | Internments | 755035 | Mdantsane Moss | 0 | 121632 | 121632 |  | Training of Councillors to be conducted | Training of Councillors to be conducted | Training of Councillors to be conducted |  | 121632
|  |  |  | 0 | 773114.79 | 773114.79 |  |  |  |  | 0 | 773114.79
10. Finance Management Grant
Finance and Support Services | Budget Office | 315005 | Budget Reforms | 1450000 |  | 1450000 | Roll Overs from 2009/10 |  |  |  | -1450000 | 0 | Funding Re-Allocated
Finance and Support Services | Supply Chain Management | 320010 | Internal Control | 0 |  | 0 |  |  |  |  | 500000 | 500000 | SCM Internal Controls and development of SCM Process Procedure and flowchart Manuals.
Finance and Support Services | Budget Office | 315005 | Interns Remuneration | 0 |  | 0 |  |  |  |  | 850000 | 850000 | Payment for Interns’ remuneration
Finance and Support Services | Budget Office | 315005 | Financial Management Training | 0 |  | 0 |  |  |  |  | 100000 | 100000 | Funding for training
|  |  |  | 1450000 | 0 | 1450000 | 0 | 0 | 0 | 0 | 0 | 1450000
11. Finance Management Grant c/o
Finance and Support Services | Budget Office | 315005 | Financial Management Training | 0 |  | 0 |  |  |  |  | 9000 | 9000 | Roll Over from 2010/2011 Conditional Grant Approved by National Treasury on 13 Feb
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000
12. Galve c/o
Strategic Management | Development Co-Operation | 120005 | Management Co-Ordination | 0 | 733636.2 | 733636.2 | Roll Overs from 2009/10 | Project not limited to our financial year | Project not limited to our financial year | Dec 2012 |  | 733636.2
|  |  |  | 0 | 733636.2 | 733636.2 |  |  |  |  | 0 | 733636.2
13. Glasgow Partnership
Strategic Management | Development Co-Operation | 120005 | Management Co-Ordination | 0 | 264808 | 264808 | Roll Overs from 2009/10 | Project not limited to our financial year | Project not limited to our financial year | Dec 2012 |  | 264808
|  |  |  | 0 | 264808 | 264808 |  |  |  |  | 0 | 264808
14. Human Settlements Development Grant (HSDG)
Municipal Services | Housing Department | 255005 | Second Creek (Turn key)-P5 | 20914860 |  | 20914860 | [5 empty] | 20914860 | The project still undergoing bid assemenet process, an award is anticipated to be made by March 2012.
Municipal Services | Housing Department | 255005 | Potsdam Unit P,Stage 2-P5 | 67085400 |  | 67085400 |  |  |  |  | -43000000 | 24085400 | Part of the project will be taken over by the PDoHS due to non delivery by the contractor.
Municipal Services | Housing Department | 255005 | Airport / Phase 2A Construction New units-P5 | 9802100 |  | 9802100 | [5 empty] | 9802100 | rectification of existing units as well as uncomplete units
Municipal Services | Housing Department | 255005 | Storm damaged reconstruction project 988 Top structures and Rural sanitation (Emergency housing) | 8000000 |  | 8000000 |  |  |  |  | -5000000 | 3000000 | Currently the service provider is on site doing re - assessment and beneficiary registration.
Municipal Services | Housing Department | 255005 | Masibambane-P5 | 6156072 |  | 6156072 |  |  |  |  | -6156072 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Masibulele-P5 | 6313920 |  | 6313920 |  |  |  |  | -6313920 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Velwano-P5 | 7892400 |  | 7892400 |  |  |  |  | -7892400 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Chris Hani Park Phase 3-P5 | 8287020 |  | 8287020 |  |  |  |  | -8287020 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Ilinge-P5 | 3946200 |  | 3946200 |  |  |  |  | -3946200 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Gwentshe Village-P5 | 986550 |  | 986550 |  |  |  |  | -986550 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Fynbos Informal 1-P5 | 4222434 |  | 4222434 |  |  |  |  | -4222434 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Fynbos Informal 2-P5 | 3946200 |  | 3946200 |  |  |  |  | -3946200 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Ndacama-P5 | 3946200 |  | 3946200 |  |  |  |  | -3946200 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Ilitha wooden Houses-P5 | 16800000 |  | 16800000 |  |  |  |  | -16300000 | 500000 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Mathemba Vuso-P5 | 2959650 |  | 2959650 |  |  |  |  | -2959650 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Deluxolo Village-P5 | 3472656 |  | 3472656 |  |  |  |  | -3472656 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Francis Mei | 1341708 |  | 1341708 |  |  |  |  | -1341708 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Mahlangu Village-P5 | 3591042 |  | 3591042 |  |  |  |  | -3591042 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Sisulu Village-P5 | 3038574 |  | 3038574 |  |  |  |  | -3038574 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Winnie Mandela -P5 | 2959650 |  | 2959650 |  |  |  |  | -2959650 | 0 | The project is following a turnkey route of development being the role out of internal with top structures. Process has commenced for the appointment of the project management team. EIA will only be completed in August 2012.
Municipal Services | Housing Department | 255005 | Reeston Phase 3 Stage 2-P4 | 400000 |  | 400000 |  |  |  |  | -400000 | 0 | Expenditure to commence as the registration process progresses and transfer of properties start in 2012 / 2013.
Municipal Services | Housing Department | 255005 | Reeston Phase 3 Stage 2-P5 | 39462000 |  | 39462000 |  |  |  |  | -39214133 | 247867 | The remainding funding is for payment of the service provider that was on site then..
Municipal Services | Housing Department | 255005 | DVRI Pilot Project, 323 units (Mekeni,Competition site ,Haven hills) -P5 | 22132000 |  | 22132000 |  |  |  |  | -12000000 | 10132000 | Project is progressing at a slow pace with a contractor on site. At Haven Hills site 120 units are at wall plate level, 45 have been plastered, and 40 at roof level. At the Mekeni Site there are 40 units completed at wall plate level and 40 at roof level, 16 units are at practical completion, to be handed over to approved beneficiaries.
Municipal Services | Housing Department | 255005 | Braelyn Ext 10 North -P2 | 1267200 |  | 1267200 |  |  |  |  | -977200 | 290000 | Project already funded with existing funding from DVRI from the previous financial year.
Municipal Services | Housing Department | 255005 | C Section (690)-P2 | 222000 |  | 222000 |  |  |  |  | -222000 | 0 | Directorate of Development Planning is currently implementing township establishment and thereafter the engineering design will commence from April 2012.
Municipal Services | Housing Department | 255005 | Pilot C Section Triangle -P2 | 48000 |  | 48000 |  |  |  |  | -48000 | 0 | Project already funded with existing funding from DVRI from the previous financial year.
Municipal Services | Housing Department | 255005 | D Hostel-P2 | 199200 |  | 199200 |  |  |  |  | -199200 | 0 | Project already funded with existing funding from DVRI from the previous financial year.
Municipal Services | Housing Department | 255005 | Duncan Village Proper (746)-P2 | 222000 |  | 222000 | [5 empty] | 222000 | Project already funded with existing funding from DVRI from the previous financial year.
Municipal Services | Housing Department | 255005 | LU Housing Nom.School-P1 | 835200 |  | 835200 |  |  |  |  | -835200 | 0 | Engineering design can only start once the township establishment has been completed
Municipal Services | Housing Department | 255005 | LU Housing Nom.School-P2 | 278400 |  | 278400 | [5 empty] | 278400 | The project is at a biding committee stage. Appointment anticipated by end March 2012
Municipal Services | Housing Department | 255005 | Lu Housing II-P1 | 349200 |  | 349200 |  |  |  |  | -349200 | 0 | Engineering design can only start once the township establishment has been completed
Municipal Services | Housing Department | 255005 | Lu Housing II-P2 | 116400 |  | 116400 | [5 empty] | 116400 | The project is at a biding committee stage. Appointment anticipated by end March 2012
Municipal Services | Housing Department | 255005 | N2 Road Reserve 1-P1 | 1746000 |  | 1746000 |  |  |  |  | -1743000 | 3000 | Engineering design can only start once the township establishment has been completed
Municipal Services | Housing Department | 255005 | N2 Road Reserve 1-P2 | 582000 |  | 582000 | [5 empty] | 582000 | The project is at a biding committee stage. Appointment anticipated by end March 2012
Municipal Services | Housing Department | 255005 | Kei Road -Dawn-P1 | 1800000 |  | 1800000 |  |  |  |  | -1800000 | 0 | Engineering design can only start once the township establishment has been completed
Municipal Services | Housing Department | 255005 | Kei Road -Dawn-P2 | 600000 |  | 600000 | [5 empty] | 600000 | The project is at a biding committee stage. Appointment anticipated by end March 2012
Municipal Services | Housing Department | 255005 | Mdantsane Access/Buffalo-P5 | 7959053 |  | 7959053 |  |  |  |  | -7959053 | 0 | The site has been identified for TRA , Development Planning will have to submit a proposal to Council for approval and prepare a layout plan.
Municipal Services | Housing Department | 255005 | Reeston Phase 3 Stage 3-P1 | 1123356 |  | 1123356 |  |  |  |  | -623356 | 500000 | A services provider has been appointed to undertake the design and supervision of internal services.
Municipal Services | Housing Department | 255005 | Reeston Phase 3 Stage 3-P4 | 127500 |  | 127500 | [5 empty] | 127500 | Funding will be spent towards beneficiary registration.
Municipal Services | Housing Department | 255005 | Amalinda (Co-op) | 319153 |  | 319153 |  |  |  |  | -319153 | 0 | 67 displaced beneficiary families of the Amalinda Co-op project has been relocated to a site in Amalinda opposite SPCA. Temporary structures were provided by the PDoHS.
Municipal Services | Housing Department | 255005 | Amalinda (CNIP Projects) | 10852050 |  | 10852050 |  |  |  |  | -10849050 | 3000 | The Municipality is currently busy with a feasibility study for the Amalinda area. A site has been identified for township establishment for this project and the survey department has started with primary surveying.
Municipal Services | Housing Department | 255005 | Ilitha South: 439 Units -P5 | 0 |  | 0 |  |  |  |  | 3200000 | 3200000 | Funding will be spent towards completing this project.
Municipal Services | Housing Department | 255005 | Accreditation | 0 |  | 0 |  |  |  |  | 4000000 | 4000000 | The funding is mainly used for project planning and implementation capacity building.
|  |  |  | 276303348 | 0 | 276303348 | 0 | 0 | 0 | -197698821 | -197698821 | 78604527
15. Dept of Human Settlements c/o
Municipal Services | Housing Department | 255005 | Reeston Phase 3 - Stage 2 - P4 - Sales Admin & Conveyancers | 0 | 79840 | 79840 | Roll Overs from 2009/10 | Service Provider has been appointed | The access to the General Plan was delayed to be submitted to the Conveyancer to proceed with the transfer | Budget will be spent in this current financial year |  | 79840 | Housing units completed and transfer of ownership is required.
Municipal Services | Housing Department | 255005 | Reeston Phase 3 - Stage 2 - 1000 units: P1 | 0 | 266510 | 266510 | Roll Overs from 2009/10 | Service provider has been appointed, the appointment of the internal services contractor for construction is still on tender stage | The funding is for contract administration (project management) which will be used once the internal services project implementation has started | The project will be implemented over in three financial years |  | 266510 | Construction monitoring
Municipal Services | Housing Department | 255005 | 1440 Families Relocation From Duncan VIllage to Reeston | 0 | 467483.43 | 467483.43 | Roll Overs from 2009/10 | The service provider is appointed on adhoc basis when there is demand for relocation. No permanent appointment of service provider is made. | Currently experiencing challenges of illegal occupation and structural defects by PDoHS appointed Contractor (Thubelisha Homes) | Depend upon the completion of the completed units. |  | 467483.43 | Funding is for relocation purposes
Municipal Services | Housing Department | 255005 | Accreditation: Buffalo City Municipality: Housing | 0 | 798530.72 | 798530.72 | Roll Overs from 2009/10 | Not applicable | The funding is maily used for salary related costs | Budget will be spent in this current financial year |  | 798530.72 | Will fund the Integrated Sustainable Human settlement Plan (ISHSP)
Municipal Services | Housing Department | 255005 | Mdantsane Zone 18 CC - Phase 2 - Stage 1: P1 | 0 | 120074.08 | 120074.08 | Roll Overs from 2009/10 | Service provide has been appointed | Engineering design only completed for 500 units, available budget can only be spent in the current financial year. Have instructed the engineers to proceed with the engineering designs for the balance of 1,000 sites, will require budget adjustment in December 2011. Available budget to be rolled over. | The project will be implemented over in two financial years |  | 120074.08 | This funding will contribute to the payment of the EIA
Municipal Services | Housing Department | 255005 | Potsdam Unit P: 500 Units - P5 Top Structure c/o | 0 | 396416 | 396416 | Roll Overs from 2009/10 | Contractor not yet awarded | Funding was held back from Thubelisha as part of rectictification and will be utilized in the current financial year on defective units. | Budget will be spent in this current financial year |  | 396416 | Funding will be used for the remainder of the project.
Municipal Services | Housing Department | 255005 | Potsdam Unit P: 500 Units - P4 c/o | 0 | 83650 | 83650 | Roll Overs from 2009/10 | Service Provider has been appointed | Land Administration who processes property transfers experience a capacity challenge and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year |  | 83650 | Beneficiary transfering.
Municipal Services | Housing Department | 255005 | Potsdam Unit P: Stage 2: 2003 Units: P1: Engineering Design c/o | 0 | 107471.85 | 107471.85 | Roll Overs from 2009/10 | The project is almost complete | Awaiting finalization of close out report to make the final payments. | Budget will be spent in this current financial year |  | 107471.85 | For the final claim of work completed by the consultant.
Municipal Services | Housing Department | 255005 | Reeston Phase 3: Stage 1: 800 Units:Conveyancing: P4 c/o | 0 | 50000 | 50000 | Roll Overs from 2009/10 | Service Provider has not been appointed | Land Administration who processes property transfers experiencing a capacity challenge and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year |  | 50000 | Beneficiary transfering.
Municipal Services | Housing Department | 255005 | Z Soga 171 Units: P4 c/o | 0 | 50000 | 50000 | Roll Overs from 2009/10 | Service Provider has been appointed | Land Administration who processes property transfers experience a capacity challenge and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year |  | 50000 | Beneficiary transfering.
Municipal Services | Housing Department | 255005 | Z Soga 171 Units: P5 c/o | 0 | 929760.01 | 929760.01 | Roll Overs from 2009/10 | Contractor was appointed | 166 Units of the 171 are complete. The contractor is off site due to 5 undevelopable sites. The department is in the process of doing the required turkey survey to develop the sites. | Budget will be spent in this current financial year |  | 929760.01 | To complete the outstanding units and rectify defects on existing units.
Municipal Services | Housing Department | 255005 | Mdantsane Zone 18 CC - Phase 2 - Stage 1 - P1 c/o | 0 | 51734 | 51734 | Roll Overs from 2009/10 | Service provide has been appointed | Engineering design only completed for 500 units, available budget can only be spent in the current financial year. Have instructed the engineers to proceed with the engineering designs for the balance of 1,000 sites, will require budget adjustment in December 2011. Available budget to be rolled over. | The project will be implemented over in two financial years |  | 51734 | This funding will contribute as a top up to the payment of the EIA
Municipal Services | Housing Department | 255005 | Manyano & Tembeilihle - P1 c/o | 0 | 387013.2 | 387013.2 | Roll Overs from 2009/10 | Service provide has been appointed | The funding is for contract administration (project management) which was delayed by delayed appointment of internal services contractor | Budget will be spent in this current financial year |  | 387013.2 | Construction monitoring
Municipal Services | Housing Department | 255005 | Airport Phase 2A - 614 Units - P4 c/o | 0 | 20000 | 20000 | Roll Overs from 2009/10 | The service Provider has been appointed | There has been a delay in the opening of the Township register and the appointed service provider has also delayed. | Budget will be spent in this current financial year |  | 20000 | Beneficiary transfering.
Municipal Services | Housing Department | 255005 | Airport Phase 2A - 614 Units - Est. Grant c/o | 0 | 76986 | 76986 | Roll Overs from 2009/10 | Contract not awarded | The funding is for contract administration (project management) which will be used once the project implementation has started. | Budget will be spent in this current financial year |  | 76986 | Project management cost
Municipal Services | Housing Department | 255005 | Amalinda Simanyene 93 Units P4 c/o | 0 | 3596.49 | 3596.49 | Roll Overs from 2009/10 | Service Provider has been appointed | Beneficiary registration completed, Land admin still busy with transfer of properties. Available budget to be rolled over. | Budget will be spent in this current financial year |  | 3596.49 | Beneficiary transfering.
Municipal Services | Housing Department | 255005 | Amalinde Simanyene 93 Units P5 c/o | 0 | 223613.27 | 223613.27 | Roll Overs from 2009/10 | Service Provider has been appointed | Project is practical complete, contractor is still busy with the snags, upon completion the money will be spent. | Budget will be spent in this current financial year |  | 223613.27 | Completion of existing top structures
Municipal Services | Housing Department | 255005 | Second Creek Development: 300 Units- P1 c/o | 0 | 467097.39 | 467097.39 | Roll Overs from 2009/10 | Service provider appointed and engineering designs are complete. Project management still to commence. | The funding will be utilised during project implementation of both internal services and top structures for project management. The appointment of the contractor is delayed. | Budget will be spent in this current financial year |  | 467097.39 | project management cost
Municipal Services | Housing Department | 255005 | Reeston Phase 1 & 2 Stage 1B: P4 - Conveyancers c/o | 0 | 10000 | 10000 | Roll Overs from 2009/10 | Service Provider has been appointed | Land Administration who processes property transfers is experiencing capacity challenges and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year |  | 10000 | Beneficiary transfering.
Municipal Services | Housing Department | 255005 | Reeston Phase 1&2 stage 1B: 1000 Units: P5 (606 units) c/o | 0 | 1283583.47 | 1283583.47 | Roll Overs from 2009/10 | Contractor on site | Payment to the contractor was held back due slow progress on signing of happy letters by beneficiaries as some of the houses are occupied by illegal occupants. | Budget will be spent in this current financial year | -912556 | 371027.47 | Project is completed no further expenditure will be incurred.
Municipal Services | Housing Department | 255005 | Reeston Phase 1 & 2 Stage 1B:400 - Est Grant | 0 | 97933 | 97933 | Roll Overs from 2009/10 | Contractor on site | Work completed, however the payment of the service provider depends upon signing of happy letters by beneficiaries. | Budget will be spent in this current financial year |  | 97933 | Construction monitoring
Municipal Services | Housing Department | 255005 | 1440 Families Relocation From Duncan VIllage to Reeston c/o | 0 | 339187 | 339187 | Roll Overs from 2009/10 | The service provider is appointed on adhoc basis when there is demand for relocation. No permanent appointment of service provider is made. | Currently experiencing challenges of illegal occupation and structural defects by PDoHS appointed Contractor (Thubelisha Homes) | Depend upon the completion of the completed units. | -324187 | 15000 | Funding for relocation cost
Municipal Services | Housing Department | 255005 | Haven HillsSouth Pilot Project: P4 c/o | 0 | 10000 | 10000 | Roll Overs from 2009/10 | Service Provider has not been appointed | Registration is underway, done in house. Land Admin was unable to proceed with the transfers because the general plans that were outstanding have only been received recently. | Budget will be spent in this current financial year | -10000 | 0
Municipal Services | Housing Department | 255005 | TyuTyu Phase 1 : 300 units : P5 : Top Structure c/o | 0 | 2493861.58 | 2493861.58 | Roll Overs from 2009/10 | Contractor on site | Delays were experienced in the signing of the subsidy agreement which affected contractors progress claim. | Budget will be spent in this current financial year | -1100000 | 1393861.58 | Completion of existing top structures
Municipal Services | Housing Department | 255005 | TyuTyu Phase 2 : 373 units : P4 :Conv & Sales Admin c/o | 0 | 10000 | 10000 | Roll Overs from 2009/10 | Service provider is on site | Land Administration who processes property transfers is experiencing capacity challenges and the request for transfers of properties to individuals get delayed. | Budget will be spent in this current financial year |  | 10000 | Beneficiary transfering.
Municipal Services | Housing Department | 255005 | TyuTyu Phase 2 : 373 units : P5 : Top Structure c/o | 0 | 822000 | 822000 | Roll Overs from 2009/10 | Currently stagnant | BCMM housing is busy with the tender document for the appointment of the contractor to construct the remaining 100 top structures, also a letter has been sent to the Department of Human Settlement for additional funding application. | Budget should be spent within the current financial year. | -822000 | 0
Municipal Services | Housing Department | 255005 | Ilitha South : 439 units : P5 : Top Structure c/o | 0 | 767687.84 | 767687.84 | Roll Overs from 2009/10 | Contractor on site | Delays were experienced in the signing of the subsidy agreement which affected contractors progress claims. | Budget will be spent in this current financial year |  | 767687.84 | Funding for rebuilding of new and existing units
Municipal Services | Housing Department | 255005 | Dimbaza Phase 2: 1720 Units P5 Top Structure | 0 | 1112586.36 | 1112586.36 | Roll Overs from 2009/10 | Contractor on site | Delays were experienced in the signing of the subsidy agreement which affected contractors progress claims. | Budget will be spent in this current financial year | -547786 | 564800 | Completion of existing top structures
Municipal Services | Housing Department | 255005 | Storm Damaged Reconstruction : 988 Units | 0 | 197484 | 197484 |  | Professional team is on site | There were delays on tender processes. Professional team has only been appointed in July 2011. | Budget should be spent within the current financial year. |  | 197484 | reconstruction of the storm damaged houses
|  |  |  | 0 | 11724099.69 | 11724099.69 |  |  |  |  | -3716529 | 8007570.33
16. Leiden Platform
Strategic Management | Development Co-Operation | 120005 | BCM Speical Programmes Focal Areas Strategies Implementaion | 0 | 139648 | 139648 | Roll Overs from 2009/10 | Funding only received end FY10/11 for use FY11/12 | New Funding Received for FY11/12 | FY11/12 |  | 139648
Strategic Management | Development Co-Operation | 120005 | Management Coordination | 0 | 190732 | 190732 |  | New funding | New funding | DEC 2012 |  | 190732
|  |  |  | 0 | 330380 | 330380 |  |  |  |  | 0 | 330380
17. Leiden Platform c/o
Strategic Management | Special Programmes | 105030 | Special Programmes Focal Areas Administrator Project | 0 | 295701.35 | 295701.35 | Roll Overs from 2009/10 | Ongoing project- does not require SCM processes | Monthly journal for Special Programmes Project Administrator FY11/12 |  |  | 295701.35
Strategic Management | Special Programmes | 105030 | BCM Speical Programmes Focal Areas Strategies Implementaion | 0 | 190350.01 | 190350.01 | Roll Overs from 2009/10 | Funding to support ongoing activities of SPU Forums | Funding to support activities of the Youth, Women's, Older Persons and Disability Forums and the Metro AIDS Council in FY11/12 | FY11/12 |  | 190350.01
Strategic Management | Development Co-Operation | 120005 | Leiden reimbursement | 0 | 100000 | 100000 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012 |  | 100000
Strategic Management | Development Co-Operation | 120005 | Communication Solid Waste | 0 | 148782 | 148782 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012 |  | 148782
Strategic Management | Development Co-Operation | 120005 | Data Collection/River Clean-Up | 0 | 99736.31 | 99736.31 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012 |  | 99736.31
Strategic Management | Development Co-Operation | 120005 | Co-Ordination Leiden Projects | 0 | 203666.79 | 203666.79 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012 |  | 203666.79
Strategic Management | Special Programmes | 105030 | HIV/AIDS Projects Leiden | 0 | 45612.31 | 45612.31 | Roll Overs from 2009/10 | Funding ring fenced printing HIV Strategy FY11/12 | Strategy only ready for printing FY11/12 | FY11/12 |  | 45612.31
Strategic Management | Development Co-Operation | 120005 | Communication Sanitation | 0 | 40000 | 40000 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012 |  | 40000
Strategic Management | Special Programmes | 105030 | BCM Special Programme Focal Areas | 0 | 52007.75 | 52007.75 | Roll Overs from 2009/10 | Funding to support ongoing activities of SPU Forums | Funding to support activities of the Youth, Women's, Older Persons and Disability Forums and the Metro AIDS Council in FY11/12 | FY11/12 |  | 52007.75
Strategic Management | Development Co-Operation | 120005 | Leiden Flood Plain Project | 0 | 33316.55 | 33316.55 | Roll Overs from 2009/10 | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012 |  | 33316.55
|  |  |  | 0 | 1209173.07 | 1209173.07 |  |  |  |  | 0 | 1209173.07
18. LGH (Local Government Housing) c/o
Development Planning and Management | City Planning | 615070 | Duncan Village Settlement Planning | 0 | 778452 | 778452 | Roll Overs from 2009/10 | Service Providers appointed. All three projects completed their feasibility study phase. In process with draft layouts, but cannot finalize them until final decision has been taken in terms of Housing Typology, densities and erf sizes. Delays experienced in regard to this during election period. DVRI is in process to organise a meeting with DV Councillors and stake holders to resolve issue. Meeting was also delayed due to strikes. Once the housing typology, densities and erf sizes has been resolved, can layout plans be submitted to PSC Mtg and to brief new councillors. | Challenge is the issue in regard to housing typology, densities and erf sizes has not been finalized and therefore draft layouts where not possible to be finalized by end of June 2011. | End of Finacial Year 2011/2012. |  | 778452
Development Planning and Management | Land Surveying | 615085 | Yellowwoods/ Kei Roads Subdivision c/o | 0 | 698133 | 698133 | Roll Overs from 2009/10 | BSC rejected specifications. Tenders have gone to the ACM for approval of specifications. | The Department of Rural Development and Land Reform funded the projects in the interim. | One year. |  | 698133
|  |  |  | 0 | 1476585 | 1476585 |  |  |  |  | 0 | 1476585
19. Own Funds
Strategic Management | Development Co-Operation | 120005 | International Partnership | 300000 |  | 300000 | Roll Overs from 2009/10 |  |  |  |  | 300000
Strategic Management | Development Co-Operation | 120005 | African Partnership | 100000 |  | 100000 | [5 empty] | 100000
Strategic Management | Communications | 120010 | Implementation of the Communication Strategy | 200000 |  | 200000 | [5 empty] | 200000
Strategic Management | IGR | 120010 | IGR | 200000 |  | 200000 | [5 empty] | 200000
Strategic Management | GIS | 110015 | GIS on the internet | 630000 |  | 630000 |  |  |  |  | -380000 | 250000 | Declared Savings
Strategic Management | Public Participation | 120010 | PP Strategy Annual Plan | 300000 |  | 300000 | [5 empty] | 300000
Strategic Management | Special Programmes | 105030 | Economic Empowerment for targeted groups (R100,000) | 100000 |  | 100000 | [5 empty] | 100000
Strategic Management | Knowledge Management | 130005 | Capacity building | 598353 |  | 598353 | [5 empty] | 598353
Strategic Management | Executive Support Services | 105005 | City Hall Refurbishment - OPEX | 0 |  | 0 |  |  |  |  | 300000 | 300000 | To refurbish City Hall
Strategic Management | Public Participation | 120010 | Youth Advisory Centres | 0 |  | 0 |  |  |  |  | 425000 | 425000 | With the assistance of the Interim Executive Director: Finance and Support Services, the current Youth Advisory Center Officers contracts have been extended in the interim for 6 months from 1st January to 30th June 2012 whilst the metro's micro organogram is being finalized.
Strategic Management | Public Participation | 120010 | Special Programmes Focal Areas Days of Importance | 0 |  | 0 |  |  |  |  | 200000 | 200000 | Within the remaining FY11/12 there are a number of days of importance which the metro would need to commemorate and these include International Women's Day in March, Youth Month in June and build up activities for events in the next FY namely Mandela Day in July.
Strategic Management | Public Participation | 120010 | Ward Committees Out of Pocket Expenses | 0 |  | 0 |  |  |  |  | 2000000 | 2000000 | Following the establishment of the metro's Ward Committees and in line with the BCMC Resolution No. 131/11 that Ward Committees be re-imbursed for their costs but may not be salaried.
Strategic Management | Public Participation | 120010 | LOGO - Public Consultation process | 0 |  | 0 |  |  |  |  | 200000 | 200000 | BCMM needs to roll-out its newly approved branding.
Finance and Support Services | Customer Care | 330020 | Online receipting system | 0 |  | 0 |  |  |  |  | 510000 | 510000 | Upgrading of batch receipting system to avoid erroneous disconnections due to delayed updates of cash to debtors accounts.
Finance and Support Services | Debtors Management Office | 330010 | Data cleanup Project | 1000000 |  | 1000000 |  |  |  |  | 1000000 | 2000000 | Additional Funding to be utilised to address under Billing(asp AG Report)
Finance and Support Services | Debtors Management Office | 330010 | Analysis of the Billing Debt book | 1000000 |  | 1000000 |  |  |  |  | -1000000 | 0 | Declared Savings to be utilised to address under Billing as raised in the AG Report
Finance and Support Services | Debtors Management Office | 330010 | Property data alignment and clean up | 500000 | -500000 | 0 |  | Funding wrongly allocated to Financial Service Budget and need to be transferred to GIS unit cost Centre | Bid Advertising closed on 23 September 2011 - the tender evaluation process in progress. Need to review one bidder for responsiveness;. | This is phase 1 of a 3 year contract Intergrated Property Information Management System and Business Process. To be completed at the end of June 2012. |  | 0
Finance and Support Services | GIS Unit | 110015 | Property data alignment and clean up | 0 | 500000 | 500000 |  | New Project - funding misallocated under Financial Service Budget. Contract CE 102 - Bid Closing date 23 September 2011. In process of functionality Evaluation. | Bid Advertising closed on 23 September 2011 - the tender evaluation process in progress. Need to review one bidder for responsiveness;. | This is phase 1 of a 3 year contract Intergrated Property Information Management System and Business Process.Phase 1 to be completed at the end of June 2012. |  | 500000
Finance and Support Services | Asset and Risk | 320005 | Accounting Reforms | 720000 |  | 720000 | [5 empty] | 720000 |  | 50% to be carried over to next financial year. | 50% to be carried over to next financial year.
Finance and Support Services | Supply Chain Management | 320010 | SCM turnaround Plan | 500000 |  | 500000 | [5 empty] | 500000
Finance and Support Services | Supply Chain Management | 320010 | SCM Intenda Project | 500000 |  | 500000 | [5 empty] | 500000
Finance and Support Services | H.R. Administration | 420005 | Development of BCM Metropolitan Municipality organogram(UNDER MM'S budget) | 300000 |  | 300000 | [5 empty] | 300000
Finance and Support Services | H.R. Administration | 420005 | Implementation of the EE Plan | 150000 |  | 150000 | [5 empty] | 150000
Finance and Support Services | H.R. Administration | 420005 | Employee wellness programme | 400000 |  | 400000 | [5 empty] | 400000
Finance and Support Services | Administration & Council Support Services | 415005 | Review BY-Law in Standing Rules of Order | 25000 |  | 25000 | [5 empty] | 25000
Finance and Support Services | Administration & Council Support Services | 415005 | Policy on Closure of Council meetings | 25000 |  | 25000 | [5 empty] | 25000
Development Facilitation and Partnership | Transportation | 620005 | BCM ITP review | 1000000 |  | 1000000 |  |  |  |  | -200000 | 800000 | Savings R200,000 Balance for Freight Transport Plan. Award has been made and consultant is progressing with project | Award has been made and consultant is progressing with project | Award has been made and consultant is progressing with project
Development Planning and Management | Spatial Planning | 615005 | Township Establishment Programme | 500000 |  | 500000 |  |  |  |  | -108677 | 391323 | Savings - Excess budget over contract amount | To be used for Phase 2 of the project | To be used for Phase 2 of the project
Development Facilitation and Partnership | SMME Development | 635005 | Business Management Training Program | 100000 |  | 100000 | [5 empty] | 100000
Development Facilitation and Partnership | SMME Development | 635005 | Emerging contractor Training Program | 400000 |  | 400000 | [5 empty] | 400000
Development Facilitation and Partnership | SMME Development | 635005 | Corporate governance Training Program | 100000 |  | 100000 | [5 empty] | 100000
Development Facilitation and Partnership | SMME Development | 635005 | Customer Training Program | 100000 |  | 100000 | [5 empty] | 100000
Development Facilitation and Partnership | SMME Development | 635005 | Tender Advise Training Program | 100000 |  | 100000 | [5 empty] | 100000
Development Facilitation and Partnership | SMME development | 635005 | Participation at International Trade Shows e.g Indaba, World Travel Market and ITB | 500000 |  | 500000 | [5 empty] | 500000
Development Facilitation and Partnership | SMME development | 635005 | Printing of marketing material for tourism SMME’s | 100000 |  | 100000 | [5 empty] | 100000
Development Facilitation and Partnership | SMME development | 635005 | Participation at Domestic Trade Shows e.g Kyalami Outdoor show in Johannesburg, Cape Town Getaway Show and Rand Easter Show | 300000 |  | 300000 | [5 empty] | 300000
Development Facilitation and Partnership | SMME development | 635005 | Management of business support centre’s e.g. Mdantsane One Stop Shop and Duncan Village Business Hives | 1000000 |  | 1000000 | [5 empty] | 1000000
Development Facilitation and Partnership | SMME development | 635005 | Cooperatives Support | 1000000 |  | 1000000 | [5 empty] | 1000000
Development Facilitation and Partnership | Tourism Development | 635005 | Health and Hygiene Training Program for the accommodation sector | 300000 |  | 300000 | [5 empty] | 300000
Development Facilitation and Partnership | Tourism Development | 635005 | Summer Season Program | 3000000 |  | 3000000 | [5 empty] | 3000000
Development Facilitation and Partnership | Tourism Development | 635005 | Tourism Month Celebration | 500000 |  | 500000 | [5 empty] | 500000
Development Facilitation and Partnership | Tourism Development | 635005 | Tourism marketing and events (Easter) | 1000000 |  | 1000000 | [5 empty] | 1000000
Development Facilitation and Partnership | Tourism Development | 635005 | Tourism Service Excellence Awards | 500000 |  | 500000 | [5 empty] | 500000
Development Facilitation and Partnership | Tourism Development | 635005 | Tourism SMME Support Programme | 100000 |  | 100000 | [5 empty] | 100000
Development Facilitation and Partnership | Agricultural Development | 635005 | Agriculture training and capacity building program | 500000 |  | 500000 | [5 empty] | 500000
Development Facilitation and Partnership | Agricultural Development | 635005 | Hydroponics Rollout Program | 3300000 |  | 3300000 | [5 empty] | 3300000
Development Facilitation and Partnership | Agricultural Development | 635005 | Farmer Support Services | 500000 |  | 500000 | [5 empty] | 500000
Development Facilitation and Partnership | Trade and investment | 635005 | Participation at local and International Investment and Trade Shows | 500000 |  | 500000 | [5 empty] | 500000
Development Facilitation and Partnership | Trade and investment | 635005 | Promotion key sector investment programme | 600000 |  | 600000 | [5 empty] | 600000
Development Facilitation and Partnership | Trade and investment | 635005 | Export Support Programme | 500000 |  | 500000 | [5 empty] | 500000
Development Facilitation and Partnership | Local Economic Development | 635005 | Review of Agricultural Strategy | 350000 |  | 350000 | [5 empty] | 350000
Municipal Services | Office of the Director of Engineering Services | 505005 | Ablution Blocks Duncan Village | 0 |  | 0 |  |  |  |  | 850000 | 850000 | The funds will be utilised for the payment of 52 caretakers.
Municipal Services | Law enforcement | 725020 | Crime Prevention Strategy | 1000000 | -1000000 | 0 |  | Correcting wrong Cost Centre | Correcting wrong Cost Centre | Correcting wrong Cost Centre |  | 0
Municipal Services | Law enforcement | 725015 | Crime Prevention Strategy |  | 1000000 | 1000000 |  | Correcting wrong Cost Centre | Correcting wrong Cost Centre | Correcting wrong Cost Centre |  | 1000000
Municipal Services | Law enforcement | 725015 | Security CCTV Beach Front | 0 |  | 0 |  |  |  |  | 1100000 | 1100000 | New project
Municipal Services | Traffic Services | 725020 | Traffic Safety Plan | 1000000 |  | 1000000 |  |  |  |  | -400000 | 600000 | Savings - Excess budget over contract amount
Municipal Services | Health Services | 710005 | Development & Implementation of an Air Quality Management Plan | 1000000 |  | 1000000 |  |  |  |  | -500000 | 500000 | Service provider commenced on 9 January 2012. Savings.
Municipal Services | Health Services | 710005 | Develop & Implement Municipal Health Services Delivery Plan | 2000000 |  | 2000000 |  |  |  |  | -250000 | 1750000 | Enviaged savings.
Municipal Services | Environmental Management | 755010 | Eradication of Alien Vegetation | 200000 |  | 200000 | [5 empty] | 200000
Municipal Services | Environmental Management | 755010 | BCM Climate Change Strategy | 350000 |  | 350000 |  |  |  |  | -100000 | 250000 | R100 000 savings anticipated. Multi year project.
Municipal Services | Environmental Management | 755010 | Environmental Education Strategy | 200000 |  | 200000 | [5 empty] | 200000
Municipal Services | Environmental Management | 755010 | Integrated Environmental Management Plan & Integrated Coastal Zone Management Plan | 350000 |  | 350000 | [5 empty] | 350000
Strategic Management | Public Participation | 120010 | Special Programmes | 0 |  | 0 |  |  |  |  | 350000 | 350000 | Additional Funding Required for Special Programmes Committees
Finance and Support Services | Rates and Valuations Office | 330005 | General valuations | 0 |  | 0 |  |  |  |  | 1000000 | 1000000 | Funding Required for General Valuations
|  |  |  | 30498353 | 0 | 30498353 | 0 | 0 | 0 | 0 | 4996323 | 35494676
20. Own Funds c/o
Strategic Management | GIS | 110015 | Cadastral Clean up and Maintenance | 240000 | 172964 | 412964 | Roll Overs from 2009/10 | Contract 2701. 3rd Year of maintenance phase of contract. Require a Total of R240,000 for the final year of contract. July, Augus, September 2011 Invoices submitted and cadastral data received. October to June 2012 invoice to be submitted as data is received and review. | The total budget for 3 years was transferred during the 2009/2010 budget adjustment process therefore a carry over for subsequent years was needed. Contractor gets paid as data is received and reveiwed. Adequate funding is required for the final year of the contract. R240 000 or R20 000 per month. | 25 June 2012 |  | 412964
Strategic Management | Public Participation | 120010 | Customer satisfaction survey | 350000 |  | 350000 | [5 empty] | 350000
Strategic Management | Development Co-Operation | 120005 | Logo South Projects Management and coordination | 37878.77 | 17718 | 55596.77 |  | Project not limited to BCMM financial year | Project not limited to BCMM financial year | DEC 2012 |  | 55596.77
Strategic Management | Executive Support Services | 105005 | Ducatts - Sewerage | 40000 | -40000 | 0 |  | Busy with DCS regarding the contracts for trained staff |  |  |  | 0
Finance and Support Services | Debtors Management Office | 330015 | Billing Debt Book c/o | 2997237 | -174845 | 2822392 |  | Funds Carry Over. Project at design/processing Phase. | Delays in Contract/Bid assessment to final award | Project contract awared April 2011 and is continuing to 2011/12 Financial year end. |  | 2822392
Finance and Support Services | Debtors Management Office | 330015 | Billing Data Clean Up c/o | 1495497 |  | 1495497 | [5 empty] | 1495497
Finance and Support Services | Asset and Risk | 320005 | Grap Implementation Project | 150000 | 76379 | 226379 |  | Contract ongoing - to be finalized 31/12/11 | The reason for the roll-over is that the service provider who is paid on a time-input basis was utilized less than what was expected. R150 000 is still required until the project completion date of 31/12/11. | Project to be completed by 31/12/11 |  | 226379
Finance and Support Services | Rates and Valuations Office | 330005 | General valuations | 4758821.9 | -729841 | 4028980.9 |  | Project to be advertised in the November 2011 and Appointment by March 2012 | Provision of Funding pre -adverrtising | Project life 18-mths. Funds to be utilised for Supplementary Valuations 05 & 06 |  | 4028980.9
Finance and Support Services | Rates and Valuations Office | 330005 | Supplementary Valuations | 241178.1 | -241178 | 0.1 |  | SV 04 performed internally | Fourth Supplementary Valuation withdrawn | Project withdrawal, SV04 |  | 0.1
Municipal Services | Office of the Director of Engineering Services | 505005 | Maintain Ablution Blocks in Informal Areas (EPWP) | 2000000 | -2000000 | 0 | [5 empty] | 0
Development Facilitation and Partnership | Local Economic Development | 635005 | Tourism Business Support | 600000 | 240889 | 840889 |  | The service provider has been appointed and has commenced . The first payment has been made to the service provider. | The votes were blocked in the first quarter and were only open in the third quarter. This caused a delay in appointing the service provider. | The project will be completed by end of march in 2012. |  | 840889
Development Facilitation and Partnership | Local Economic Development | 635005 | Heritage and Tourism Route | 594193 | -100510 | 493683 |  | The service provider to implement the project has been appointed and has commenced with the implementation. The first payment has already been made to the service provider. | The votes were blocked in the first quarter and were only open in the third quarter. This caused a delay in appointing the service provider. | The project will be completed by the end of May. |  | 493683
Development Facilitation and Partnership | Local Economic Development | 635005 | Economic Planning | 300000 | 23093 | 323093 |  | The service provider to implement the project has been appointed and has commenced with the implementation. The first payment has already been made to the service provider. | The votes were blocked in the first quarter and were only open in the third quarter. This caused a delay in appointing the service provider. | The project will be completed at the end of April 2012. |  | 323093
Development Facilitation and Partnership | Local Economic Development | 635005 | Urban Agriculture | 493614 | -419803 | 73811 |  | Project is on going, request for informal tender for Dimbaza Agric coops in in progress to provide agricultural infraSTRUCTURE. Service provider was asppointed who could not deliver the required services. | Informal tender request for inputs | 1 month after budget Approval by Council |  | 73811
Development Facilitation and Partnership | Local Economic Development | 635005 | Cooperative Support Fund | 412863 | -338600 | 74263 |  | Project in progrss for Poultry Cooperative, structure finalised towards end June and therefore remaining funds to be utilised for operational inputs | Informal tender request for inputs | 1 month after budget Approval by Council |  | 74263
Development Facilitation and Partnership | Local Economic Development | 635005 | Informal Traders Development Programme | 381821 | -262497 | 119324 | [5 empty] | 119324
Development Facilitation and Partnership | Local Economic Development | 635005 | Trade and Investment | 485000 |  | 485000 | [5 empty] | 485000
Development Planning and Management | Transport Planning | 620005 | SDF Review & Implementation | 250000 | 3684 | 253684 |  | Consultants are appointed and project is underway with data analysis. It has been requested on a number of occasions that this be moved to the City Planning Cost Centre. Invoices have been received and can only be paid once roll-overs have been implemented. | Apointments were only finalised in June 2011. Finance indicated that the money could be rolled over if the funding was committed before the end of the FY. Funding was committed and appointments were made. No challenges | Project will be completed December 2011 | -35312 | 218372 | Data analysis phase of the SDF mapping nearly completed and which will feed into the SDF Review for the entire BCMM. | Busy with data analysis phase of SDF mapping | Busy with data analysis phase of SDF mapping
Development Facilitation and Partnership | Transport Planning | 620005 | Transport planning | 1497438 | -795776 | 701662 |  | ITP review at Bid Evaluation stage. Tender awarded for Non-motorised Transport study | ITP Review:Tender award has been made and project to commence. Delays were caused by key staff shortages and funding not being released until 3rd quarter. NMT Study: Delays in signing Service Level Agreement, delays in councilors being appointed on Project Steering Committee | ITP review: Project to be completed by 31 March 2011 NMT Study: May 2012 |  | 701662
Development Facilitation and Partnership | Transport Planning | 620005 | Transport policy and by-law | 305464 | -35464 | 270000 |  | Tender was requested to be cancelled | Delays caused by tender validity not being extended. Extension was required due to KZN ruling and other procurement delays (Bid Evaluation Committee requested SCM to provide report on preferred supplier capacity). Tender has been re-advertised and closes on 21 October 2011. | Project to be completed by 30 April 2012 |  | 270000
Development Planning and Management | City Planning | 615070 | Vincent Berea Riview | 0 | 306140 | 306140 |  | Consultants are appointed and project is underway with data analysis. Invoices have been received and can only be paid once the roll-overs have been implemented. This project has been left off the rollover budget and finance has been requested several times to put it back. Therefore the division has included it. | Apointments were only finalised in June 2011. Finance indicated that the money could be rolled over if the funding was committed before the end of the FY. Funding was committed and appointments were made. No challenges. | Project will be completed December 2011 | -104900 | 201240 | Busy with data analysis phase of office and retail and industrial land use study for Vincent Berea and other areas of BCMM. This portion of analysis will feed into SDF Review for entire BCMM | Busy with data analysis phase of office and retail and industrial land use study for Vincent Berea and other areas of BCMM. This portion of analysis will feed into SDF Review for entire BCMM | Busy with data analysis phase of office and retail and industrial land use study for Vincent Berea and other areas of BCMM. This portion of analysis will feed into SDF Review for entire BCMM
Municipal Services | Disaster Management | 725055 | Disaster Management Structures | 236218 | -1830 | 234388 |  | Service provider appointed | D.M. Structure funding utilised for D.M. Framework Policy | March 2012 |  | 234388
Municipal Services | E.L. Regional Waste Disposal Sites & Transfer Station | 770030 | Intergrated Waste Management Plan of Buffalo City | 747255 |  | 747255 |  |  |  |  | -669030 | 78225 | Award has been made and consultant is progressing with project.
Municipal Services | Zoo | 765025 | Section 78 Studies for the Zoo, Aquarium | 179298 |  | 179298 | [5 empty] | 179298
Strategic Management | Municipal Manager and Support Services | 205005 | Metro Status Impact Analysis | 0 | 990765.56 | 990765.56 | [5 empty] | 990765.56
[7 empty] | Roll Overs from 2009/10 |  |  |  |  | 0
|  |  |  | 18793776.77 | -3308711.44 | 15485065.33 |  |  |  |  | -809242 | 14675823.33
21. Urban Settlement Development Grant (USDG)
Municipal Services | Housing Projects | 255005 | Mdantsane Zone 18 CC Phase 2-P4 | 127500 |  | 127500 | Roll Overs from 2009/10 |  |  |  |  | 127500
Municipal Services | Housing Projects | 255005 | Manyano & Thembelihle Phase 2-P4 | 680000 |  | 680000 |  |  |  |  | -680000 | 0
Municipal Services | Housing Projects | 255005 | Second Creek (Turn key )-P4 | 212000 |  | 212000 |  |  |  |  | -212000 | 0
Municipal Services | Housing Projects | 255005 | Potsdam unit ,Stage 2 - P4 | 783265 |  | 783265 |  |  |  |  | -733265 | 50000 | The budget is for transfers. I
Municipal Services | Housing Projects | 255005 | Airport / Phase 2A Construction of new units-P4 | 156570 |  | 156570 |  |  |  |  | -106570 | 50000 | Budget is for beneficiary transfers.
Municipal Services | Housing Projects | 255005 | Masibambane-P4 | 19890 |  | 19890 | [5 empty] | 19890 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Masibulele-P4 | 20655 |  | 20655 | [5 empty] | 20655 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Velwano-P4 | 25500 |  | 25500 | [5 empty] | 25500 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Chris Hani Park Phase 3-P4 | 26775 |  | 26775 | [5 empty] | 26775 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Ilinge-P4 | 25500 |  | 25500 | [5 empty] | 25500 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Gwentshe Village-P4 | 6375 |  | 6375 | [5 empty] | 6375 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Westbank Restitution-P1 | 7293600 |  | 7293600 | [5 empty] | 7293600 | Will be contributing towards engineering design funding
Municipal Services | Housing Projects | 255005 | Westbank Restitution-P2 | 2431200 |  | 2431200 |  |  |  |  | -2431200 | 0 | Township establishment has been completed.
Municipal Services | Housing Projects | 255005 | Fynbos Informal 1-P2 | 256800 |  | 256800 | [5 empty] | 256800 | Site is currently being surveyed
Municipal Services | Housing Projects | 255005 | Fynbos Informal 1-P4 | 27285 |  | 27285 | [5 empty] | 27285 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Fynbos Informal 2-P2 | 1105200 |  | 1105200 | [5 empty] | 1105200 | Site is currently being surveyed
Municipal Services | Housing Projects | 255005 | Fynbos Informal 2-P4 | 25500 |  | 25500 | [5 empty] | 25500 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Ndacama-P2 | 768000 |  | 768000 | [5 empty] | 768000 | Site is currently being surveyed
Municipal Services | Housing Projects | 255005 | Ndacama-P4 | 25500 |  | 25500 | [5 empty] | 25500 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Mathemba Vuso-P4 | 19125 |  | 19125 | [5 empty] | 19125 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Deluxolo Village-P4 | 22440 |  | 22440 | [5 empty] | 22440 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Francis Mei-P4 | 8670 |  | 8670 | [5 empty] | 8670 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Mahlangu Village-P4 | 23205 |  | 23205 | [5 empty] | 23205 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Sisulu Village-P4 | 19636 |  | 19636 | [5 empty] | 19636 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Winnie Mandela-P4 | 38250 |  | 38250 | [5 empty] | 38250 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Dacawa | 38250 |  | 38250 | [5 empty] | 38250 | Budget is for beneficiary registration.
Municipal Services | Housing Projects | 255005 | Sunny South-P4 | 25500 |  | 25500 | [5 empty] | 25500 | Budget is for beneficiary registration.
|  |  |  | 14212191 | 0 | 14212191 |  |  |  |  | -4163035 | 10049156
22. SALAIDA c/o
Strategic Management | Development Co-Operation | 120005 | GAVLE Projects 2008-2009 | 0 | 738298.33 | 738298.33 | Roll Overs from 2009/10 | Project not limited to BCM financial year | 10 year anniversary in February 2012 | Dec. 2012 |  | 738298.33
|  |  |  | 0 | 738298.33 | 738298.33 |  |  |  |  | 0 | 738298.33
23. SETA c/o
Finance and Support Services | Organisational Development | 420020 | Training and Development | 0 | 10282.14 | 10282.14 | Roll Overs from 2009/10 | Preparations for local government elections negatively affected availability of targeted councilors | Preparations for local government elections negatively affected availability of targeted councilors | Preparations for local government elections negatively affected availability of targeted councilors |  | 10282.14
Strategic Management | Councillors | 105012 | Councillor Training | 0 | 1145430.7 | 1145430.7 | Roll Overs from 2009/10 | Funding had to be reserved for orientation and induction of newly elected councillors | Funding had to be reserved for orientation and induction of newly elected councillors | Funding had to be reserved for orientation and induction of newly elected councillors |  | 1145430.7
|  |  |  | 0 | 1155712.84 | 1155712.84 |  |  |  |  | 0 | 1155712.84
24. Trust Funds c/o
Development Planning and Management | City Planning | 615070 | Planning - Potsdam Unit V | 0 | 127492 | 127492 | Roll Overs from 2009/10 | Service Providers have been appointed. Final draft layout plans completed and circulated for comments to line departments. Extensive delays in project completion due to very slow or no response of receiving of comments from critical technical department. Various reminders and requests for comments have been unsuccessful to date. Once all comments have been received can layout be finalised and submitted to council for approval. | Challenge is that comments from key line departments are still outstanding in regard to the final draft layout which has been circulated beginning of the year. | End of December 2011 and the to be submitted to Council beginning of 2012. |  | 127492
Development Planning and Management | City Planning | 615070 | Map Preparation | 0 | 127492 | 127492 | Roll Overs from 2009/10 | Project linked to the Informal Settlement Study & Implementation Programme for the printing of maps and documents of the final report once approved by Council | None | End of financial year 2011/2012 |  | 127492
|  |  |  | 0 | 254984 | 254984 |  |  |  |  | 0 | 254984
|  |  |  | 356719667.77 | 22318718.38 | 379038385.15 | 0 | 0 | 0 | -197698821 | -197113668 | 181924716.79

## Summary
OPEX PER FUNDING SOURCE | 2011/2012 | 2011/2012 | 2011/2012 | 2011/2012 | 2011/2012
| APPROVED | BUDGET | 1st ROLL-OVER | BUDGET | MID YEAR
| BUDGET | ADJUSTMENTS | ADJ. BUDGET | ADJUSTMENTS | ADJ. BUDGET
NEW PROJECTS
Own Funds | 30498353 | 0 | 30498353 | 4996323 | 35494676
Finance Management Grant | 1450000 | 0 | 1450000 | 0 | 1450000
Urban Settlement Development Grant | 14212191 | 0 | 14212191 | -4163035 | 10049156
Glasgow Partnership | 0 | 264808 | 264808 | 0 | 264808
Human Settlement Development Grant | 276303348 | 0 | 276303348 | -197698821 | 78604527
Leiden Platform | 0 | 330380 | 330380 | 0 | 330380
Dept of Water Affairs and Forestry - DoRA | 2830000 | 0 | 2830000 | 34000 | 2864000
Dept of Water Affairs and Forestry - Provincial | 12395000 | 0 | 12395000 | 5689085 | 18084085
TOTAL NEW OPEX PROJECTS | 337688892 | 595188 | 338284080 | -191142448 | 147141632
ROLLED-OVER PROJECTS
Disaster Mangement Fund | 96999 |  | 96999 | 0 | 96999
Own Funds | 18793777 | -3308711 | 15485066 | -809242 | 14675824
BCMET | 0 | 604382.5 | 604382.5 | 0 | 604382.5
Dept of Environmental Affairs and Tourism | 140000 | 0 | 140000 | 0 | 140000
Dept of Water Affairs and Forestry - DoRA | 0 | 0 | 0 | 4000 | 4000
Local Government and Traditional Affairs | 0 | 1256873 | 1256873 | -733110 | 523763
DLGTA | 0 | 5105381.4 | 5105381.4 | -725339 | 4380042.4
European Commission | 0 | 773114.87 | 773114.87 | 0 | 773114.87
Finance Management Grant | 0 | 0 | 0 | 9000 | 9000
Galve | 0 | 733636.2 | 733636.2 | 0 | 733636.2
Dept of Human Settlements | 0 | 11724100 | 11724100 | -3716529 | 8007571
Leiden Platform | 0 | 1209173.07 | 1209173.07 | 0 | 1209173.07
LGH (Local Government Housing) | 0 | 1476584.56 | 1476584.56 | 0 | 1476584.56
SALAIDA | 0 | 738298.33 | 738298.33 | 0 | 738298.33
SETA | 0 | 1155712.84 | 1155712.84 | 0 | 1155712.84
Trust Funds | 0 | 254984 | 254984 | 0 | 254984
TOTAL ROLLED-OVER OPEX PROJECTS | 19030776 | 21723529.77 | 40754305.77 | -5971220 | 34783085.77
TOTAL OPEX PER FUNDING SOURCE | 356719668 | 22318717.77 | 379038385.77 | -197113668 | 181924717.77
OPEX PER DIRECTORATE | 2011/2012 | 2011/2012 | 2011/2012 | 2011/2012 | 2011/2012
| APPROVED | BUDGET | 1st ROLL-OVER | BUDGET | MID YEAR
| BUDGET | ADJUSTMENTS | ADJ. BUDGET | ADJUSTMENTS | ADJ. BUDGET
Strategic Management | 3096232 | 8132024 | 11228256 |  | 11228256
Municipal Services | 315100309 | 11834212 | 326934521 |  | 326934521
Finance and Support Services | 16212734 | -547068 | 15665666 |  | 15665666
Directorate of Development Planning | 22310393 | 2899549 | 25209942 |  | 25209942
Development Planning and Management | 0 | 0 | 0 | 0 | 0
| 356719668 | 22318718 | 379038385 | 0 | 379038386